## Project Plan
Project Name: Wave Connect
Module | Start Date | End Date | Estimated Hours | Actual Hours | Developer | Status
Modules/Tasks | [5 empty] | Status
Milestone 1 | 2024-12-23 | 2024-12-29 | 45
Week 1 - Project setup, architecture flow and setup and design
Project setup for frontend: |  |  | 20
Set up React project with TypeScript,TanStack React Query,and required UI packages. |  |  | 1
Set up the basic folder structure for components, services and ESLint Setup |  |  | 3
Developing Signup Screen as per the Figma design. |  |  | 8
Developing Login Screen as per the Figma design. |  |  | 6
Private / Public routing setup |  |  | 2
Project setup for backend: |  |  | 25
API module ( Backend setup ) |  |  | 2
Common Module setup |  |  | 2
Architecture and schema setup as per HIPAA Compliance both admin |  |  | 8
Middleware setup |  |  | 3
Component and routing setup |  |  | 2
Database and schema creation |  |  | 2
API for User Sign-Up |  |  | 3
API for User Login and reset password |  |  | 3
Milestone 2 | 2024-12-30 | 2025-01-05 | 45
Week 2 - Authentication, Authorization, and Initial user interactions API
API to create waves and comments on waves including video and photo and database model |  |  | 4
API to create new friends and show friends and database model |  |  | 5
API to show all latest waves and database model |  |  | 5
API to invite and add friends |  |  | 7
API to manage waves |  |  | 7
API to show profile |  |  | 7
API to edit profile |  |  | 5
Api for searching |  |  | 5
Milestone 3 | 2025-01-06 | 2025-01-12 | 45
Week 3 - Creating user interactions pages and profile page
Dashboard Screen List of latest waves and display friends |  |  | 8
View User Profile Popup (Displaying user details in a modal) |  |  | 7
Friends List (Implementing add friends, pending/accepted status) |  |  | 8
Invite Friends Form (Email uniqueness validation, pending/accepted status) |  |  | 9
Waves Management (Creating activate/deactivate waves,maganing comments on waves) |  |  | 7
Creating profile editing form and change password |  |  | 6
Milestone 4 | 2025-01-13 | 2025-01-19 | 45
Week -4 - Admin Portal & Final Touches
API and model for Admin Register |  |  | 8
Admin Login & Register Screens |  |  | 5
Admin Dashboard (Charts of users data,pdf,CSV, manages waves, and admin control) |  |  | 6
Manage Users (View, edit, delete users, change status) |  |  | 7
Manage Waves (View, edit, delete waves, change status) |  |  | 7
Admin Comments Management (View and delete user comments) |  |  | 7
HIPAA Compliance Implementation (Audit logs, password expiry, account lockout) |  |  | 5

## Milestone Schedule
Project Release Plan
Milestone No | Sprint | No. of resources | Start Date | End Date | Release No | Milestone Acceptance date | Actual hrs burnt | Status | Acceptance Date
1 | 2 | 2 | 2024-08-26 | 2024-09-08 | ER1 | 2024-09-16
2 | 2 | 2 | 2024-09-09 | 2024-09-22 | ER2 | 2024-09-30
3 | 2 | 2 | 2024-09-23 | 2024-10-06 | ER3 | 2024-10-14
4 | 2 | 2 | 2024-10-07 | 2024-10-20 | ER4 | 2024-10-28
5 | 2 | 2 | 2024-10-21 | 2024-11-03 | ER5 | 2024-11-07

## Summary
Project Start Date | 2024-08-26
Actual End Date | 2024-10-31
Sales Person | ⁠Vishal Sagar Shahi
Revision History
Date | Author | Changes Details | Reference
2024-08-23 | Gaurav Sexena
Resource Allocation
Name | Role On Project | Alignment Date | Resource Released Date
Jashan Dhiman | Developer | 2024-08-22
Bhushan Sharma | Developer | 2024-08-22

## Ghant chart
Gantt Chart
Project Name: | Eye-Refer |  |  |  | Project Start Date |  | 2024-08-26
Project Owner: | Jashan dhiman |  |  |  | Project End Date |  | 2024-10-31
Project Lead : | Gaurav Saxena
|  |  |  | 2024-08-26 | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28
|  |  |  | M1 |  | M2 | M4 | M3 |  | M4 |  | M5
| Resources | Start date | End date | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10
Admin / Web / Api | Jashan Dhiman | 2024-08-26 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Bhushan Sharma | 2024-08-26 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
Desginer | ⁠Yashpal Chaudhary | 2024-08-26 | 31/01/24 | 2024-08-26: 40; 2024-09-02: 20; 2024-09-09: 20
Collection
Deliverables
Acceptance
Review