## Project Plan
Project Name: Wave Connect
Module | Start Date | End Date | Estimated Hours | Actual Hours | Developer | Status
Modules/Tasks | [5 empty] | Status
Milestone 1 | 2024-12-23 | 2024-12-29 | 45
Week 1 - Project setup, architecture flow and setup and design
Project setup for frontend: |  |  | 20
Set up React project with TypeScript,TanStack React Query,and required UI packages. |  |  | 1
Set up the basic folder structure for components, services and ESLint Setup |  |  | 3
Developing Signup Screen as per the Figma design. |  |  | 8
Developing Login Screen as per the Figma design. |  |  | 6
Private / Public routing setup |  |  | 2
Project setup for backend: |  |  | 25
API module ( Backend setup ) |  |  | 2
Common Module setup |  |  | 2
Architecture and schema setup as per HIPAA Compliance both admin and user |  |  | 8
Middleware setup |  |  | 3
Component and routing setup |  |  | 2
Database and schema creation |  |  | 2
API for User Sign-Up |  |  | 3
API for User Login and reset password |  |  | 3
Milestone 2 | 2024-12-30 | 2025-01-05 | 45
Week 2 - Authentication, Authorization, and Initial user interactions API
API to create waves and comments on waves including video and photo and database model |  |  | 4
API to create new friends and show friends and database model |  |  | 5
API to show all latest waves and database model |  |  | 5
API to invite and add friends |  |  | 7
API to manage waves |  |  | 7
API to show profile |  |  | 7
API to edit profile |  |  | 5
Api for searching |  |  | 5
Milestone 3 | 2025-01-06 | 2025-01-12 | 45
Week 3 - Creating user interactions pages and profile page
Dashboard Screen List of latest waves and display friends |  |  | 8
View User Profile Popup (Displaying user details in a modal) |  |  | 7
Friends List (Implementing add friends, pending/accepted status) |  |  | 8
Invite Friends Form (Email uniqueness validation, pending/accepted status) |  |  | 9
Waves Management (Creating activate/deactivate waves,maganing comments on waves) |  |  | 7
Creating profile editing form and change password |  |  | 6
Milestone 4 | 2025-01-13 | 2025-01-19 | 45
Week -4 - Admin Portal & Final Touches
API and model for Admin Register |  |  | 8
Admin Login & Register Screens |  |  | 5
Admin Dashboard (Charts of users data,pdf,CSV, manages waves, and admin control) |  |  | 6
Manage Users (View, edit, delete users, change status) |  |  | 7
Manage Waves (View, edit, delete waves, change status) |  |  | 7
Admin Comments Management (View and delete user comments) |  |  | 7
HIPAA Compliance Implementation (Audit logs, password expiry, account lockout) |  |  | 5